## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Responsible Person | Status | Budget Allocated (USD) | Actual Cost (USD) | Variance (USD)
T001 | Project Planning Phase | 2024-03-01 | 2024-03-15 | 15 | Sarah Johnson | Completed | $15,000 | $14,200 | $800 (Under)
T002 | Market Research & Analysis | 2024-03-16 | 2024-04-10 | 35 | David Kim | In Progress | $22,500 | $18,900 | $3,600 (Under)
T003 | Product Design & Prototyping | 2024-04-11 | 2024-05-31 | 61 | Lisa Chen | Planned | $45,000 | $0.00 | $45,000 (Over)
T004 | Development & Testing Phase | 2024-06-01 | 2024-08-31 | 90 | Mike Turner | Not Started | $120,000 | $0.00 | $120,000 (Over)