## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Duration (Days) | Priority | Status | Estimated Cost | Actual Cost
T-001 | Product Launch Preparation | Sarah Thompson | 2024-03-15 | 2024-04-15 | 31 | High | In Progress | $15,000 | $12,800
T-002 | Market Research Survey | James Lee | 2024-03-20 | 2024-04-10 | 19 | Medium | Completed | $8,500 | $8,500
T-003 | Website Redesign Phase 1 | Alex Chen | 2024-03-25 | 2024-05-15 | 61 | High | Pending | $22,000 | -
T-004 | Customer Onboarding Process | Maria Garcia | 2024-04-01 | 2024-05-31 | 60 | Medium | Not Started | $18,000 | -
T-005 | Quarterly Performance Review | David Kim | 2024-04-10 | 2024-05-10 | 31 | Low | Scheduled | $5,200 | -
Total Estimated Cost |  |  |  |  | $60,700 | $31,300