## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | Priority | Budget (USD) | Actual Cost (USD) | Remaining Budget (USD)
T001 | Project Planning Phase | Jane Doe | 2024-03-15 | 2024-03-25 | 11 | Completed | High | 15,000.00 | 14,250.00 | 750
T002 | UI/UX Design Finalization | Alex Chen | 2024-03-26 | 2024-04-10 | 15 | In Progress | Medium | 8,000.00 | 4,200.00 | 3,800.00
T003 | Backend Development | Sam Patel | 2024-04-11 | 2024-05-30 | 51 | Not Started | High | 45,000.00 | 0 | 45,000.00
T004 | Testing & Quality Assurance | Mia Rodriguez | 2024-06-01 | 2024-06-30 | 30 | Planned | Medium | 12,000.00 | 0 | 12,000.00