## Worksheet
Page | Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Resource Assigned | Priority | Status | Dependencies
1 | TS-001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | High | Completed
1 | TS-002 | Requirements Gathering | 2024-04-02 | 2024-04-15 | 14 | Business Analysts | High | In Progress | TS-001
2 | TS-003 | UI/UX Design Phase | 2024-04-16 | 2024-05-10 | 35 | Design Team | Medium | Pending Start | TS-002
2 | TS-004 | Frontend Development | 2024-05-11 | 2024-06-30 | 60 | Frontend Developers | High | Not Started | TS-003
3 | TS-005 | Backend Integration | 2024-07-01 | 2024-07-31 | 31 | Backend Engineers | High | Not Started | TS-004
3 | TS-006 | Testing & QA Phase | 2024-08-01 | 2024-08-31 | 31 | QA Team | Medium | Not Started | TS-005
Multi-Page Task Scheduling – Cash Flow Statement Style