## Worksheet
Task ID | Task Name | Scheduled Date | Assigned To | Priority Level | Status | Estimated Duration (Days) | Budget Allocation ($) | Actual Cost ($)
T001 | Project Kickoff Meeting | 2023-10-05 | John Smith | High | Completed | 1 | 500 | 480
T002 | Market Research Phase | 2023-10-10 | Anna Lee | Medium | In Progress | 7 | 3,500.00 | 1,850.00
T003 | Design Finalization | 2023-10-25 | Mike Chen | High | Pending | 14 | 7,000.00 | 0
T004 | Development Phase | 2023-11-05 | Sara Williams | High | Not Started | 30 | 15,000.00 | 0
T005 | Quality Assurance Testing | 2023-11-20 | David Park | Medium | Planned | 10 | 4,000.00 | 0