## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority Level | Status | Estimated Duration (Days) | Budget Allocation ($)
T001 | Market Research Phase | 2024-04-01 | 2024-04-15 | Jane Doe | High | Pending | 15 | 5,000.00
T002 | Product Design Finalization | 2024-04-16 | 2024-05-10 | John Smith | High | In Progress | 35 | 12,000.00
T003 | Development Phase - Backend | 2024-05-11 | 2024-06-30 | Alex Brown | Medium | Not Started | 60 | 25,000.00
T004 | User Testing & Feedback Loop | 2024-07-01 | 2024-07-31 | Samantha Lee | Medium | Planned | 30 | 8,000.00
T005 | Launch Preparation & Marketing | 2024-08-01 | 2024-08-31 | Marcus White | High | Not Started | 30 | 15,000.00