## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Responsible Person | Status | Priority Level | Estimated Budget (USD)
T-001 | Project Kickoff Meeting | 2024-03-05 | 2024-03-05 | 1 | Jane Doe | On Track | High | 500
T-002 | Market Research Phase | 2024-03-06 | 2024-03-18 | 13 | John Smith | On Track | Medium | 3,500.00
T-003 | Prototype Development | 2024-03-19 | 2024-04-05 | 17 | Alice Johnson | Pending | High | 8,000.00
T-004 | User Testing & Feedback | 2024-04-06 | 2024-04-15 | 10 | Michael Brown | On Track | Medium | 4,200.00
T-005 | Final Review & Deployment | 2024-04-16 | 2024-04-30 | 25 | Sarah Lee | Planned | High | 7,500.00