## Worksheet
Quarter | Task Name | Scheduled Start Date | Scheduled End Date | Responsible Party | Resource Allocation | Status | Budget (USD) | Actual Spend (USD)
Q1 | Project Kickoff Meeting | 2023-04-01 | 2023-04-05 | Project Manager | Full-Time (2 days) | On Track | 500 | 480
Q1 | Market Research Phase | 2023-04-06 | 2023-05-31 | Research Lead | Part-Time (4 weeks) | In Progress | 2,500.00 | 2,100.00
Q2 | Design Finalization | 2023-06-01 | 2023-07-15 | Design Team | Full-Time (6 weeks) | On Track | 4,000.00 | 3,950.00
Q2 | Development Sprint | 2023-07-16 | 2023-09-30 | Engineering Team | Full-Time (12 weeks) | On Track | 8,000.00 | 7,920.00
Q3 | Testing & Quality Assurance | 2023-10-01 | 2023-11-30 | QA Manager | Full-Time (8 weeks) | On Track | 3,500.00 | 3,475.00
Q3 | User Training Sessions | 2023-12-01 | 2023-12-31 | Training Coordinator | Part-Time (3 weeks) | On Track | 800 | 790
Q4 | Final Review & Deployment | 2024-01-01 | 2024-02-28 | Project Manager & Ops Team | Full-Time (6 weeks) | On Track | 2,000.00 | 1,980.00