## Worksheet
Task ID | Task Name | Due Date | Assigned To | Status | Priority | Estimated Hours | Actual Hours | Budgeted Cost | Actual Cost
T-001 | Product Requirement Analysis | 2023-10-15 | Alex Rivera | In Progress | High | 8 | 6 | $1,200 | $900
T-002 | UI/UX Design Finalization | 2023-11-05 | Samira Chen | Pending | High | 12 | 0 | $2,400 | $0
T-003 | Backend API Development | 2023-11-20 | David Kim | In Progress | Medium | 16 | 10 | $3,200 | $2,500
T-004 | Frontend Implementation | 2023-12-10 | Jasmine Patel | Not Started | Medium | 18 | 0 | $3,600 | $0
T-005 | Performance Optimization | 2024-01-15 | Marcus Reed | Planned | Low | 6 | 0 | $900 | $0