## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Responsible Person | Status | Estimated Duration (Days) | Budget Allocated ($) | Actual Cost ($)
T001 | Project Initiation Meeting | 2024-04-01 | 2024-04-01 | Sarah Johnson | Completed | 1 | 500 | 480
T002 | Market Research Phase | 2024-04-02 | 2024-04-15 | Mark Davis | In Progress | 14 | 3,500.00 | 2,800.00
T003 | Product Design Finalization | 2024-04-16 | 2024-05-10 | Lisa Chen | Planned | 35 | 12,000.00 | 0
T004 | Development Sprint 1 | 2024-05-11 | 2024-06-15 | James Wilson | Pending Approval | 45 | 18,000.00 | 9,200.00
T005 | User Testing & Feedback | 2024-06-16 | 2024-07-15 | Anna Rodriguez | Not Started | 30 | 6,000.00 | 0