## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (days) | Status | Priority | Estimated Cost | Actual Cost
T001 | Project Planning Workshop | Alex Johnson | 2024-04-01 | 2024-04-03 | 3 | Completed | High | 1,500.00 | 1,480.00
T002 | UI/UX Design Finalization | Sara Chen | 2024-04-05 | 2024-04-15 | 11 | In Progress | Medium | 3,200.00 | 2,850.00
T003 | Backend Development Phase | David Kim | 2024-04-16 | 2024-05-10 | 35 | Not Started | High | 12,000.00 | 0
T004 | QA Testing & Bug Resolution | Lisa Park | 2024-05-11 | 2024-05-30 | 20 | Planned | Medium | 4,500.00 | 0
Total Estimated Cost |  |  |  |  | 21,200.00 | 18,180.00