## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority Level | Status | Budget Allocation ($) | Actual Cost ($) | Remaining Budget ($)
T001 | Project Planning Meeting | 2023-10-05 | 2023-10-05 | John Smith | High | Completed | 500 | 480 | 20
T002 | Design Phase Kickoff | 2023-10-10 | 2023-10-15 | Sarah Johnson | Medium | In Progress | 2,000.00 | 850 | 1,150.00
T003 | Development Phase Start | 2023-10-18 | 2023-11-15 | Mike Brown | High | Not Started | 8,000.00 | 0 | 8,000.00
T004 | QA & Testing Review | 2023-11-20 | 2023-11-25 | Lisa Davis | Medium | Scheduled | 1,500.00 | 0 | 1,500.00
T005 | Final Deployment & Handover | 2023-12-01 | 2023-12-05 | Tom Wilson | High | Not Started | 3,000.00 | 0 | 3,000.00
Total Budget Allocated |  |  |  | $15,000.00 |  | - | $15,000.00 | $2,330.00 | $12,670.00