## Worksheet
Task ID | Task Name | Scheduled Start Date | Planned End Date | Duration (Days) | Assigned Resource | Budget Allocation ($) | Actual Start Date | Actual End Date | Status | Remaining Budget ($) | Cash Flow Impact
TSK-001 | Market Research Phase | 2024-03-15 | 2024-03-30 | 15 | Analyst A | 5,000 | — | — | Pending | 5,000 | +5,000 (Outflow)
TSK-002 | Product Design Development | 2024-04-01 | 2024-05-15 | 65 | Designer B & C | 30,000 | 2024-04-05 | 2024-05-12 | On Track | 1,500 | +30,000 (Outflow)
TSK-003 | Prototype Testing | 2024-05-162024-06-10 | 35 | Engineer D | 15,000 | 2024-05-18 | 2024-06-08 | On Track | 1,000 | +15,000 (Outflow)
TSK-004 | Client Review & Final Approval | 2024-06-11 | 2024-06-25 | 14 | Manager E | 8,000 | 2024-06-13 | 2024-06-24 | Completed | 0 | +8,000 (Outflow)
TSK-005 | Post-Launch Support Setup | 2024-07-01 | 2024-07-31 | 31 | Support Team F | 6,000 | — | — | Not Started | 6,000 | +6,000 (Planned Outflow)