## Worksheet
Task ID | Task Name | Scheduled Date | Due Date | Status | Assigned To | Estimated Cost | Actual Cost (if any) | Progress (%)
TSK-001 | Project Planning & Scope Finalization | 2024-03-15 | 2024-03-30 | On Track | Anna Smith | $5,000 | $4,800 | 96%
TSK-002 | Market Research & Competitive Analysis | 2024-03-20 | 2024-04-10 | Pending | James Lee | $8,000 | - | 30%
TSK-003 | UI/UX Design Phase | 2024-04-05 | 2024-05-15 | Overdue | Linda Chen | $15,000 | $13,500 | 80%
TSK-004 | Backend Development Setup | 2024-04-15 | 2024-06-01 | On Track | Marcus Brown | $30,000 | $29,800 | 99%
TSK-005 | Performance Testing & Optimization | 2024-06-10 | 2024-07-30 | Planned | Sarah Wilson | $7,500 | - | 0%