## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Assigned To | Priority | Status | Budget Allocation ($) | Actual Spend ($) | Cash Flow Variance ($)
T001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | John Doe | High | Completed | 500 | 480 | 20
T002 | Market Research Phase | 2024-03-16 | 2024-03-31 | 16 | Jane Smith | Medium | In Progress | 3,500.00 | 2,800.00 | 700
T003 | Product Design Finalization | 2024-04-01 | 2024-04-15 | 15 | Alex Johnson | High | Pending | 8,000.00 | - | -
T004 | Development Phase (Beta) | 2024-04-16 | 2024-05-31 | 57 | Team A | Critical | Not Started | 15,000.00 | - | -
T005 | QA & Testing | 2024-06-01 | 2024-06-30 | 30 | Sarah Lee | High | Planned | 6,000.00 | - | -
Total Budget Allocated |  |  |  |  | 33,000.00 | 28,280.00 | +4,720.00