## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Responsible Person | Resource Allocation | Budget Assigned ($) | Cash Flow Status | Progress (%)
T001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | John Smith | Project Manager | 2,000.00 | Paid | 100%
T002 | Requirements Gathering | 2024-03-16 | 2024-03-31 | 16 | Lisa Chen | Business Analysts (2) | 8,500.00 | Pending | 45%
T003 | Design Phase | 2024-04-01 | 2024-04-15 | 15 | Mike Johnson | UX & UI Design Team | 12,000.00 | Pending | 20%
T004 | Development Phase | 2024-04-16 | 2024-06-30 | 75 | Sarah Kim | Development Team (8) | 45,000.00 | Not Started | 0%
T005 | Testing & Quality Assurance | 2024-07-01 | 2024-07-31 | 31 | David Brown | QA Engineers (4) | 9,000.00 | Not Started | 0%