## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Assigned Team Member | Priority Level | Budget Allocation ($) | Expected Cash Flow In ($) | Expected Cash Flow Out ($) | Net Cash Flow ($) | Status | Dependencies
T-001 | Market Research Phase | 2024-03-15 | 2024-03-31 | 17 | Sara Chen | High | 5,000.00 | 3,200.00 | 1,800.00 | 1,400.00 | On Track | None
T-002 | Product Development Sprint | 2024-04-01 | 2024-05-15 | 56 | Mark Thompson | Critical | 25,000.00 | 18,500.00 | 6,500.00 | 12,000.00 | Pending Review | T-001 Completion
T-003 | Beta Testing & Feedback Loop | 2024-05-16 | 2024-06-10 | 35 | Lisa Rodriguez | Medium | 8,000.00 | 4,900.00 | 3,100.00 | 1,800.00 | In Progress | T-002 Completion
T-004 | Launch Campaign Preparation | 2024-06-11 | 2024-07-31 | 61 | James Kim | High | 30,000.00 | 22,000.00 | 8,556.78 | 13,443.22 | On Hold | T-003 Completion
T-005 | Post-Launch Evaluation | 2024-08-01 | 2024-08-31 | 31 | Anna Patel | Low | 4,500.00 | 2,800.00 | 1,700.00 | 1,100.00 | Planned | T-004 Completion