## Worksheet
Task ID | Task Name | Start Date | End Date | Scheduled Hours | Assigned To | Status | Budget (USD) | Actual Spend (USD) | Cash Flow Impact
T001 | Project Planning Phase | 2024-03-15 | 2024-03-20 | 8 | John Doe | Completed | 1,500.00 | 1,475.00 | 25
T002 | Requirement Gathering | 2024-03-21 | 2024-03-28 | 16 | Jane Smith | In Progress | 3,000.00 | 2,850.00 | 150
T003 | UI/UX Design Review | 2024-03-29 | 2024-04-05 | 12 | Alice Johnson | Pending | 2,200.00 | 0 | -2,200.00
T004 | Development Phase (Phase 1) | 2024-04-06 | 2024-04-18 | 32 | Bob Lee | Scheduled | 8,000.00 | 0 | -8,000.00
T005 | QA Testing & Feedback | 2024-04-19 | 2024-04-30 | 18 | Carol White | Not Started | 3,500.00 | 0 | -3,500.00
Total |  |  |  | 86 |  |  | 18,200.00 | 7,325.00 | +10,875.00