## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Responsible Person | Resource Allocation | Budget Assigned ($) | Cash Flow Type | Status | Priority Level | Dependencies
T-001 | Project Initiation & Planning | 2024-03-15 | 2024-03-25 | 10 | John Doe | Full Team (Project Manager) | 15,000 | Inflow | On Track | High | None
T-002 | Market Research & Analysis | 2024-03-26 | 2024-04-10 | 15 | Sarah Lee | Analytics Team (3 members) | 8,500 | Outflow | On Track | Medium | Depends on T-001
T-003 | Product Design Finalization | 2024-04-11 | 2024-05-15 | 35 | Mike Chen | Design Team (Full) | 20,000 | Inflow | On Track | High | Depends on T-002
T-004 | Development & Coding Phase | 2024-05-16 | 2024-07-30 | 85 | Emma Rodriguez | Engineering Team (12 members) | 95,000 | Outflow | At Risk | Critical | Depends on T-003
T-005 | QA Testing & Bug Fixing | 2024-08-01 | 2024-08-31 | 31 | David Kim | QA Team (5 members) | 7,000 | Inflow | On Track | Medium | Depends on T-004
T-006 | Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 15 | Anna Patel | Operations & DevOps Team | 5,000 | Inflow | Pending Review | High | Depends on T-005