## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Responsible Person | Status | Budget Allocated ($) | Actual Spend ($) | Cash Flow Impact
T001 | Market Research Phase | 2024-03-15 | 2024-03-25 | 10 | Sarah Lee | Completed | 5,000.00 | 4,800.00 | +200.00 (Inflow)
T002 | Product Design Finalization | 2024-03-26 | 2024-04-10 | 15 | James Wong | In Progress | 12,000.00 | 8,500.00 | +3,500.00 (Inflow)
T003 | Development Sprint 1 | 2024-04-11 | 2024-04-25 | 15 | Team A (Lead: Alex Kim) | Not Started | 20,000.00 | 0 | -20,000.00 (Outflow Pending)
T004 | Quality Assurance Testing | 2024-04-26 | 2024-05-10 | 15 | Lisa Chen | Planned | 6,500.00 | 0 | -6,500.00 (Outflow Pending)
Summary |  |  |  |  | Total Cash Flow Impact
Total Tasks: 4 |  |  |  |  | $43,500.00 | $13,300.00 | +30,200.00 (Net Inflow)