## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Responsible Party | Estimated Duration (Days) | Status | Budget Allocation ($) | Cash Flow Impact
TSK-001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | Project Manager | 1 | Completed | $500 | +500 (Initial Investment)
TSK-002 | <Market Research Phase | 2024-04-03 | 2024-04-15 | Research Team | 13 | In Progress | $8,000 | +8,000 (Ongoing)
TSK-003 | Product Design Finalization | 2024-04-18 | 2024-05-10 | Design Lead | 23 | Pending Approval | $15,000 | +15,000 (Future)
TSK-004 | Development Sprint 1 | 2024-05-11 | 2024-05-31 | Engineering Team | 31 | Not Started | $25,000 | +25,000 (Forecast)
TSK-005 | QA Testing & Validation | 2024-06-15 | 2024-06-30 | QA Manager | 16 | Planned | $7,500 | +7,500 (Scheduled)