## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Resource Assigned | Priority Level | Status | Estimated Cost | Actual Cost (if available)
T001 | Project Kickoff Meeting | 2023-10-01 | 2023-10-01 | 1 | Project Manager | High | Completed | $500.00 | $500.00
T002 | Market Research Phase | 2023-10-02 | 2023-10-15 | 14 | Research Team | Medium | In Progress | $3,000.00 | $2,500.00
T003 | Design Finalization | 2023-10-16 | 2023-10-28 | 13 | UI/UX Designer | High | Planned | $4,500.00 | $0.00
T004 | Development Sprint 1 | 2023-10-29 | 2023-11-05 | 7 | Development Team | High | Scheduled | $8,000.00 | $0.00
T005 | Testing & QA Review | 2023-11-06 | 2023-11-18 | 13 | QA Team | Medium | <Scheduled | $5,200.00 | $0.00
T006 | Client Review & Approval | 2023-11-19 | 2023-11-25 | 7 | Project Manager & Client | High | Planned | $2,000.00 | $0.00
Total Scheduled Tasks |  |  |  | 51 | Total Estimated Cost |  | $23,200.00 | Total Actual Cost (to date) |  | $5,000.00