## Worksheet
Task | Scheduled Start Date | Scheduled End Date | Duration (Days) | Responsible Person | Status | Budget Allocation (USD) | Cash Flow Impact
Project Planning Meeting | 2024-03-01 | 2024-03-01 | 1 | John Doe | Completed | 500 | +500.00 (Initial)
Resource Allocation Review | 2024-03-05 | 2024-03-07 | 3 | Jane Smith | In Progress | 2,000.00 | +2,000.00 (Ongoing)
Development Phase Kickoff | 2024-03-10 | 2024-03-31 | 30 | Mike Johnson | Pending | 8,000.00 | +8,000.00 (Projected)
Quality Assurance Testing | 2024-04-05 | 2024-04-15 | 10 | Sarah Lee | Planned | 3,500.00 | +3,500.00 (Scheduled)
Final Review & Go-Live | 2024-04-20 | 2024-04-25 | 6 | David Kim | Pending | 2,500.00 | +2,500.00 (Final)