## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Duration (Days) | Responsible Person | Priority Level | Status | Allocated Budget | Actual Cash Flow
T001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Alice Johnson | High | Completed | $500.00 | $500.00
T002 | Market Analysis Phase | 2024-03-16 | 2024-03-31 | 16 | Bob Smith | Medium | In Progress | $3,200.00 | $2,150.00
T003 | Design Finalization | 2024-04-01 | 2024-04-15 | 15 | Carol Davis | High | Pending | $4,800.00 | $0.00
T004 | Development Phase | 2024-04-16 | 2024-05-31 | 46 | David Lee | Critical | Not Started | $12,000.00 | $0.00
T005 | Quality Assurance Testing | 2024-06-01 | 2024-06-15 | 15 | Eve Martinez | High | Planned | $3,000.00 | $0.00
Total Scheduled Tasks: |  |  |  | 107 | Total Allocated Budget: $23,500.00 ¦ Total Actual Cash Flow: $2,650.00