## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority Level | Estimated Duration (Days) | Budget Allocation ($) | Current Status | Progress (%)
T001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | J. Smith | High | 1 | 500 | Completed | 100%
T002 | Requirements Gathering | 2024-04-02 | 2024-04-15 | A. Johnson | High | 14 | 8,000.00 | In Progress | 65%
T003 | System Design Phase | 2024-04-16 | 2024-05-10 | M. Lee | Medium | 25 | 15,000.00 | Pending Approval | 20%
T004 | Development Sprint 1 | 2024-05-11 | 2024-06-15 | R. Patel | High | 35 | 22,000.00 | Not Started | 0%
T005 | User Acceptance Testing | 2024-07-01 | 2024-07-31 | L. Chen | Medium | 30 | 9,500.00 | Planned | 0%
Summary |  |  |  |  | Total Tasks | Total Budget ($) | Average Duration (Days)
— |  |  |  |  | 5 | 54,500.00 | 21.6