## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Duration (Days) | Status | Budget Allocation | Actual Cost | Cash Flow Impact
T-001 | Project Kickoff Meeting | Team Lead | 2024-03-01 | 2024-03-01 | 1
T-002 | Requirement Gathering | Business Analyst | 2024-03-02 | 2024-03-15
T-003 | Design Phase Review | UI/UX Designer | 2024-03-16 | 2024-03-25
T-004 | Development Sprint 1 | Development Team | 2024-03-26 | 2024-04-15
T-005 | Testing and QA | QA Lead | 2024-04-16 | 2024-04-30
T-006 | Deployment & Go-Live | Operations Team | 2024-05-01 | 2024-05-03
Total Tasks: |  |  |  | 6 | Avg Duration: | 15.2 | Total Budget: | $30,000 | Total Cash Flow: | $28,500