## Worksheet
Week | Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority | Status | Estimated Cost | Actual Cost (USD)
Week 1 | TSK-001 | Project Kickoff Meeting | 2023-10-02 | 2023-10-04 | Jane Doe | High | Completed | $500.00 | $500.00
Week 2 | TSK-002 | Market Research Analysis | 2023-10-09 | 2023-10-13 | John Smith | Medium | In Progress | $1,200.00 | $850.00
Week 3 | TSK-003 | UI/UX Design Review | 2023-10-16 | 2023-10-20 | Linda Chen | High | <Pending | $3,500.00 | $0.00
Week 4 | TSK-004 | Development Sprint 1 | 2023-10-23 | 2023-10-27 | Marcus Bell | High | Not Started | $8,000.00 | $0.00
Week 5 | TSK-005 | Quality Assurance Testing | 2023-10-30 | 2023-11-03 | Sophia Lee | Medium | Scheduled | $2,400.00 | $0.00