## Worksheet
Task ID | Client Name | Project Name | Task Description | Assigned To | Start Date | Due Date | Status | Priority Level | Estimated Hours | Actual Hours | Progress % | Notes
TSK-001 | Alpha Solutions Inc. | Mobile App Development | Design UI/UX for mobile application with user onboarding flow. | Sarah Johnson | 2024-04-01 | 2024-05-15 | In Progress | High | 80 | 60 | 75% | Finalize wireframes before client review.
TSK-002 | Global Tech Partners | Cloud Migration Project | Migrate legacy systems to AWS with minimal downtime. | Michael Chen | 2024-04-10 | 2024-06-30 | Not Started | Critical | 150 | 0 | 0% | Requires security audit and vendor approval.
TSK-003 | Bright Future Agency | Digital Marketing Campaign | Launch social media campaign targeting Gen Z audience. | Lisa Patel | 2024-04-15 | 2024-05-31 | On Track | Medium | 40 | 35 | 87.5% | Ad budget approved; creative assets ready.
TSK-004 | InnovateX Ltd. | AI Integration for CRM | Integrate AI chatbot into customer relationship management system. | David Kim | 2024-05-01 | 2024-07-15 | Planned | High | 120 | 0 | 0% | Needs requirements finalization from product team.