## Worksheet
Task ID | Client Name | Project Phase | Scheduled Start Date | Scheduled End Date | Status | Responsible Team | Budget Allocation (USD) | Priority Level
TSK-001 | GlobalTech Solutions | Development Phase | 2024-04-01 | 2024-06-30 | On Track | Engineering Team | 150,000.00 | High
TSK-002 | BrightFuture Inc. | Design Review | 2024-03-15 | 2024-04-30 | Completed | Design Team | 75,000.00 | Medium
TSK-003 | NexGen Analytics | Pilot Launch | 2024-05-01 | 2024-07-15 | Pending Approval | Product Team | 120,000.00 | High
TSK-004 | Alpha Innovations | Compliance Audit | 2024-05-10 | 2024-06-15 | In Progress | Legal & Compliance | 50,000.00 | Medium