## Worksheet
Task ID | Task Description | Assigned To | Due Date | Priority | Status | Estimated Cost | Actual Cost | Progress (%) | Responsible Department
TSK-001 | Client onboarding process setup | Jane Smith | 2024-04-15 | High | In Progress | $2,500.00 | $1,800.00 | 72% | Customer Success
TSK-002 | Quarterly financial review meeting | Michael Chen | 2024-05-10 | Moderate | Pending Approval | $3,200.00 | $0.00 | 35% | Finance Team
TSK-003 | CRM system migration to cloud platform | Sarah Lee | 2024-06-30 | High | Not Started | $15,000.00 | $0.00 | 0% | IT Department
TSK-004 | Monthly sales performance report generation | Alex Brown | 2024-04-30 | Low | Completed | $1,200.00 | $1,200.00 | 100% | Sales Operations
TSK-005 | Update client contract templates | Linda Wong | 2024-05-20 | Moderate | In Review | $850.00 | $575.00 | 67% | Legal & Compliance