## Worksheet
Task ID | Task Description | Scheduled Date | Priority Level | Assigned To | Estimated Duration (hours) | Status | Dependencies | Progress (%) | Notes
T001 | Finalize Q3 Financial Reports | 2023-10-15 | High | Sarah Chen | 40 | In Progress | T002, T003 | 65% | Ensure all departmental data is validated before submission.
T002 | Review Budget Allocation for Operations | 2023-10-18 | Medium | James Wilson | 25 | Not Started | T004 | 0% | Compare with last quarter's spending patterns.
T003 | Conduct Vendor Performance Audit | 2023-11-05 | High | Linda Park | 35 | Planned | None | 0% | Include cost-benefit analysis for each vendor.
T004 | Update Risk Management Framework | 2023-11-10 | High | Michael Torres | 50 | Pending Review | T002, T005 | 20% | Align with new compliance requirements.
T005 | Prepare Annual Staff Training Plan | 2023-12-01 | Medium | Emily Davis | 45 | Not Started | T006 | 0% | Include diversity and inclusion modules.