## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Resources Required | Dependents
T001 | Project Kickoff Meeting | Team Lead A | 2024-04-01 | 2024-04-03 | High | In Progress | Meeting Room, 2 participants | -
T002 | Requirement Gathering Phase | Analyst B
T003 | Design Review Meeting | Designer C | 2024-04-15 | 2024-04-17 | Medium | Planned | Design Tools, 3 participants | T002
T004 | Development Sprint 1 | Dev Team D | 2024-04-20 | 2024-05-15 | High | Pending Start | Codebase, CI/CD Tools | T003
T005 | QA Testing Phase | QA Engineer E | 2024-05-20 | 2024-06-10 | High | Not Started | Test Cases, Automation Suite | T004