## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Estimated Hours | Actual Hours | Budgeted Cost | Actual Cost | Notes
T001 | Project Planning Meeting | Jane Doe | 2024-04-01 | 2024-04-03 | High | Completed | 8 | 8.5 | $400 | $425 | Initial project scope defined and approved.
T002 | UI/UX Design Phase | John Smith | 2024-04-05 | 2024-04-15 | Medium | In Progress | 20 | 12 | $1,500 | $900 | Design mockups finalized for review.
T003 | Backend Development | Alex Turner | 2024-04-16 | 2024-05-10 | High | Not Started | 40 | 0 | $2,000 | $0 | Development framework setup pending.