## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Estimated Hours | Actual Hours | Budgeted Cost | Actual Cost
TSK-001 | Project Planning Phase | John Doe | 2024-03-15 | 2024-03-25 | High | In Progress | 8 | 6.5 | $800.00 | $650.00
TSK-002 | Design Finalization | Sarah Kim | 2024-03-26 | 2024-04-10 | Medium | Not Started | 12 | 0 | $1,200.00 | $0.00
TSK-003 | Development Sprint 1 | Mike Chen | 2024-04-11 | 2024-04-25 | High | On Track | 16 | 15.2 | $1,600.00 | $1,520.00
TSK-004 | Testing & QA Review | Lisa Wong | 2024-04-26 | 2024-05-15 | Medium | Scheduled | 10 | 0 | $1,000.00 | $0.00