## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Budget (USD) | Actual Cost (USD) | Notes
T001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | Completed | High | 500 | 485 | Initial team alignment and scope definition.
T002 | Market Research Phase | John Smith | 2024-04-05 | 2024-04-15 | In Progress | Medium | 1,200.00 | 750 | Conducting surveys and competitor analysis.
T003 | Development Sprint 1 | Team Alpha | 2024-04-16 | 2024-04-30 | Planned | High | 8,500.00 | - | UI/UX design and backend setup.
T004 | Client Review Session | Sarah Lee | 2024-05-01 | 2024-05-01 | Scheduled | High | 1,000.00 | - | Final approval of prototype before launch.