## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours
T001 | Project Planning Meeting | John Smith | 2024-04-15 | 2024-04-16 | Completed | Medium | 4 | 4
T002 | UI Design Finalization | Sarah Lee | 2024-04-17 | 2024-04-23 | In Progress | High | 16 | 8.5
T003 | Backend API Development | Michael Chen | 2024-04-20 | 2024-05-10 | Pending | High | 32 | 0
T004 | User Testing Phase | Lisa Wong | 2024-05-15 | 2024-05-25 | Not Started | Medium | 10 | 0