## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Estimated Hours | Actual Hours | Budgeted Cost | Actual Cost | Progress (%) | Notes
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | High | Completed | 2 | 2 | $150.00 | $150.00 | 100% | Initial planning and team alignment.
T002 | Requirement Gathering Workshop | Jane Smith | 2024-04-03 | 2024-04-05 | High | In Progress | 6 | 3.5 | $420.00 | $210.00 | 58% | Team discussions with stakeholders; draft requirements in progress.
T003 | Design Phase Final Review | Mike Johnson | 2024-04-10 | 2024-04-15 | Medium | Pending | 8 | 0 | $640.00 | $0.00 | 0% | Awaiting approval from client design team.
T004 | Development Sprint 1 | Team A | 2024-04-16 | 2024-04-30 | High | Scheduled | 32 | 0 | $2,560.00 | $0.00 | 0% | Development begins in next sprint cycle.