## Worksheet
Task Name | Assigned To | Due Date | Priority | Status | Estimated Hours | Actual Hours
Project Planning Meeting | John Doe | 2024-04-10 | High | In Progress | 4 | 3.5
Design UI Mockups | Jane Smith | 2024-04-15 | Medium | Not Started | 8 | 0
Develop Backend API | Alex Brown | 2024-04-25 | High | Completed | 12 | 12
User Testing Phase | Sara Lee | 2024-05-01 | Medium | Scheduled | 6 | 0