## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Estimated Hours | Actual Hours | Budget (USD) | Remaining Budget
T-001 | Project Planning Meeting | Jane Doe | 2024-04-15 | 2024-04-16 | High | Completed | 8 | 8 | 400 | 0
T-002 | Design Phase Review | John Smith | 2024-04-18 | 2024-04-25 | Medium | In Progress | 16 | 5 | 800 | 750
T-003 | Development Sprint 1 | Team A | 2024-04-26 | 2024-05-03 | High | Planned | 40 | 0 | 2,000.00 | 2,000.00
T-004 | User Testing Session | Lisa Brown | 2024-05-10 | 2024-05-15 | Low | Pending Approval | 6 | 0 | 300 | 300