## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Estimated Hours | Actual Hours
T-001 | Project Planning Meeting | John Doe | 2024-04-01 | 2024-04-01 | High | Completed | 2.5 | 2.5
T-002 | Requirement Gathering | Jane Smith | 2024-04-03 | 2024-04-10 | Medium | In Progress | 15 | 8
T-003 | UI/UX Design Phase | Alex Lee | 2024-04-11 | 2024-04-25 | High | Planned | 30 | 0
T-004 | Backend Development | Mike Brown | 2024-05-01 | 2024-05-31 | High | Not Started | 80 | 0