## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Notes
T001 | Project Planning Meeting | John Smith | 2024-04-01 | 2024-04-01 | Completed | Medium | 2.5 | 2.5 | Review project scope and timeline.
T002 | Design Phase Final Review | Sarah Johnson | 2024-04-05 | 2024-04-10 | In Progress | High | 8 | 5 | Client feedback required on UI mockups.
T003 | Development Sprint 1 | Mike Davis | 2024-04-11 | 2024-04-18 | Planned | High | 20 | 0 | First coding iteration to be completed.
T004 | User Testing Session | Emily Chen | 2024-04-25 | 2024-04-27 | Scheduled | Medium | 6 | 0 | Validate functionality with end users.