## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Estimated Hours | Actual Hours
T001 | Project Planning Meeting | J. Smith | 2024-04-01 | 2024-04-03 | High | Completed | 8 | 7.5
T002 | Design Phase Review | A. Johnson | 2024-04-05 | 2024-04-10 | Medium | In Progress | 12 | 6
T003 | Development Sprint 1 | M. Davis | 2024-04-11 | 2024-04-18 | High | Pending | 40 | 0
T004 | User Testing Session | L. Wilson | 2024-04-20 | 2024-04-25 | Medium | Scheduled | 16 | 0