## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Estimated Hours | Actual Hours | Notes
T001 | Design UI Mockups | Team Lead - Alex Johnson | 2024-04-01 | 2024-04-15 | High | In Progress | 20 | 15 | Include responsive design for mobile and tablet.
T002 | Develop Backend API | Developer - Sam Rivera | 2024-04-05 | 2024-04-30 | High | Not Started | 35 | 0 | Integrate user authentication and role-based access.
T003 | Test All Features | QA Engineer - Jordan Lee | 2024-04-10 | 2024-05-15 | Medium | Planned | 30 | 0 | Run smoke, regression, and performance tests.
T004 | Prepare Project Documentation | Team Member - Taylor Park | 2024-04-18 | 2024-05-10 | Low | Not Started | 15 | 0 | Include user manuals and developer guides.