## Worksheet
Task ID | Task Name | Scheduled Date | Due Date | Priority Level | Responsible Person | Budget Allocation ($) | Status | Progress (%) | Remarks
TS-001 | Quarterly Financial Review | 2024-03-15 | 2024-03-31 | High | Finance Manager | 15,000.00 | On Track | 85% | Preparation of variance analysis reports.
TS-002 | Budget Revisions for Q2 | 2024-04-01 | 2024-05-15 | Medium | Finance Analyst | 8,500.00 | Pending Approval | 30% | Waiting for departmental input.
TS-003 | Annual Audit Preparation | 2024-06-01 | 2024-11-30 | High | Internal Auditor | 25,000.00 | Not Started | 0% | Full documentation and compliance review required.
TS-004 | Expense Reporting System Upgrade | 2024-05-10 | 2024-07-31 | Medium | IT Finance Liaison | 12,000.00 | In Progress | 65% | Testing phase completed; deployment scheduled.