## Worksheet
Task ID | Task Name | Responsible Party | Start Date | End Date | Duration (Days) | Budget Allocation | Status | Priority Level
TSK-001 | Project Kickoff Meeting | Project Manager | 2024-03-15 | 2024-03-15 | 1 | $5,000 | On Track | High
TSK-002 | Budget Finalization | Finance Director | 2024-03-16 | 2024-03-25 | 10 | $15,000 | In Progress | High
TSK-003 | Resource Allocation Plan | Operations Lead | 2024-03-26 | 2024-04-05 | 10 | $8,500 | Planned | Medium
TSK-004 | Q1 Financial Review | Accounting Team | 2024-04-10 | 2024-04-15 | 6 | $3,750 | Pending Approval | Medium
TSK-005 | Final Reporting & Closeout | Project Manager | 2024-05-01 | 2024-05-15 | 15 | $7,200 | Not Started | Low