## Worksheet
Task ID | Task Name | Scheduled Date | Due Date | Priority | Responsible Person | Status | Estimated Cost | Actual Cost
T-001 | Market Research Phase | 2024-03-15 | 2024-03-30 | High | Alex Morgan | On Track | $5,000 | $4,800
T-002 | Product Prototype Development | 2024-04-05 | 2024-05-15 | Medium | Jordan Lee | In Progress | $15,000 | $9,200
T-003 | User Testing & Feedback Loop | 2024-05-20 | 2024-06-10 | High | Mia Patel | Planned | $8,500 | $0
T-004 | Launch Marketing Campaign | 2024-07-01 | 2024-07-31 | Medium | Taylor Chen | Pending Approval | $7,000 | $0
T-005 | Post-Launch Analytics Review | 2024-08-15 | 2024-08-30 | Low | Sam Rivera | Not Started | $3,000 | $0