## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Budget (USD) | Actual Cost (USD) | Remaining Budget | Priority
TSK-001 | Q1 Financial Forecasting | Jane Smith | 2024-03-01 | 2024-03-31 | Completed | 15,000.00 | 14,250.00 | 750 | High
TSK-002 | Monthly Expense Review | John Doe | 2024-04-01 | 2024-04-30 | In Progress | 5,000.00 | 3,850.00 | 1,150.00 | Medium
TSK-003 | Year-End Audit Preparation | Lisa Chen | 2024-05-01 | 2024-06-30 | Pending Approval | 25,000.00 | 0 | 25,000.00 | High
TSK-004 | Payroll System Upgrade | Robert Kim | 2024-06-01 | 2024-07-31 | Scheduled | 18,500.00 | 0 | 18,500.00 | Critical
TSK-005 | Vendor Contract Review | Sarah Lee | 2024-07-152024-08-31 | Pending Approval | 3,200.00 | 1,950.00 | 1,250.00 | Medium