## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget (USD) | Actual Cost (USD) | Progress (%) | Responsible Team
TSK-001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-03 | 3 | High | Completed | 5,000.00 | 4,850.00 | 100% | Project Leadership
TSK-002 | Market Analysis Phase | Jane Smith | 2024-04-05 | 2024-05-15 | 41 | Medium | In Progress | 25,000.00 | 18,230.50 | 65% | Strategy Team
TSK-003 | UI/UX Design Finalization | Alex Johnson | 2024-05-16 | 2024-06-10 | 35 | High | Scheduled | 12,000.00 | 0 | 0% | Design Team
TSK-004 | Development Sprint 1 | Sam Patel | 2024-06-11 | 2024-07-15 | 35 | High | Pending Approval | 80,000.00 | 42,567.30 | 45% | Engineering Team
TSK-005 | Quality Assurance Testing | Mia Lee | 2024-07-16 | 2024-08-10 | 35 | Medium | Scheduled | 15,000.00 | 0 | 0% | QA Team