## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | Budget (USD) | Actual Cost (USD) | Variance (%)
TSK-001 | Project Planning Workshop | Jane Doe | 2024-04-01 | 2024-04-05 | 5 | Completed | 1,500.00 | 1,475.00 | -1.67%
TSK-002 | UI/UX Design Phase | John Smith | 2024-04-06 | 2024-04-18 | 13 | In Progress | 8,500.00 | 6,200.00 | -27.1%
TSK-003 | Backend Development | Alex Chen | 2024-04-19 | 2024-05-15 | 37 | Scheduled | 25,000.00 | - | -
TSK-004 | QA Testing & Review | Sara Kim | 2024-05-16 | 2024-05-31 | 16 | Pending Approval | 7,200.00 | - | -
TSK-005 | Deployment & Launch | Team Lead | 2024-06-01 | 2024-06-05 | 5 | Not Started | 3,800.00 | - | -
Total Budget |  |  |  |  | 46,000.00 | 18,875.00 | -32.9%