## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Estimated Cost | Actual Cost | Budget Variance
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | High | Completed | $500.00 | $480.00 | +$20.00
TSK-002 | Requirements Finalization | Mark Johnson | 2024-04-05 | 2024-04-15 | Medium | In Progress | $3,500.00 | $2,850.00 | +$650.00
TSK-003 | UI/UX Design Phase | Lisa Chen | 2024-04-16 | 2024-05-05 | High | Pending | $8,000.00 | $0.00 | +$8,000.00
TSK-004 | Development Sprint 1 | Team Alpha | 2024-05-06 | 2024-05-31 | High | Scheduled | $15,000.00 | $0.00 | +$15,000.00
TSK-005 | Client Review & Sign-off | Sarah Williams | 2024-06-01 | 2024-06-15 | High | Not Started | $4,500.00 | $0.00 | +$4,500.00